## Slide 1: Project : Mobile Phone
Members of the group:
Feras Sameer Saleem
Adulrahman Abdallah Adam
Mohammed Ghasan Alqunbar
Mohammed Adel Alghzzawi
Ibrahem Adel Alghzzawi
Osaid abdulqader daghash

## Slide 2: Kick-off Meeting Agenda
Project Name: Mobile Phone
Objective of the meeting: Effectively start the project by defining the role of each member of the group, reviewing the project objectives, and discussing future plans
Agenda:
Introductions of attendees
Review of the project background
Review of project-related documents
Discussion of project organizational structure
Discussion of project scope, time, and cost goals
Discussion of other important topics
List of action items from meeting
Date: 15/11/2022
Action Item | Assigned To | Due Date
Project interface design | Mohammed | 17/12/2022
Project Interior design | Abdulrahman | 17/12/2022
programmer | Feras | 17/12/2022
Problem analysis | Mohammed Adel | 17/12/2022
solving problems | Ibrahem | 17/12/2022
Project Interior design | osaid | 17/12/2022
Date Of Next Meeting: 24/11/2022

## Slide 3: Mind Map of a SWOT Analysis to Help Identify Potential Projects
Attractive design
Strong sales and interpersonal skills
Always Availability
Strong technical/software skills
Current client wants us to bid on project
Industry continues to grow
Two major conferences
No sales experience
No clear marketing strategy
needs big capital
Lots of competition
Several more established competitors
High risk business
Providing suitable offers
Sales experince
Marketing plan
Project proposal
Conference promotions
Weaknesses
Threats
Opportunities
Strengths
SWOT Analysis

## Slide 4: Net Present Value

## Slide 5: JWD Consulting NPV Example

## Slide 6: Charting the Payback Period
Chart: 
| 0 | 1 | 2 | 3 | 0 | 1 | 2 | 3
Y-Values | 0 | 180000 | 350000 | 530000 | 150000 | 180000 | 210000 | 250000

## Slide 7: Project Charter
Project title: Mobile Phone
Date of authorization: 10/11/2022
Project start date: 10/11/2022 Project finish date: 20/1/2023
Key schedule milestones:
Finish first meeting: 12/11/2022
Finish first version of design: 3/12/2022
Finish programming: 15/12/2022
Finish testing: 10/1/2023
Finish project: 20/1/2023
Budget information: Budget information: The company has allocated 45,000 dollars for this project, because it requires a lot of equipment, there is cooperation with external sources, and more money can be paid if necessary.
Project manager: Feras Sameer, 0785713559,AD0039@iu.edu.jo

## Slide 8: Project Charter
Project goal:
1- Facilitate the purchasing process
2- Introducing the advantages of each phone
3- Encouraging customers
4- Facilitate the person's selection of the phone
5- The financial income of the shop owner
Major project success Criteria:
1- When the site performs all the tasks to be done
2- When customers like it
3- When it is easy for customers to buy
4- When he achieves an actual financial income for the owner of the shop

## Slide 9: Project Charter
Approach:
1- Not assigning any task to the employee from a different project in order to maintain focus
2- Finishing the theoretical part in a short period of time and allocating time for the practical part that the user deals with in order to avoid the problems that he may face.
3- Conduct weekly progress review meetings with the core and sponsor project team.
4- Comprehensive testing of the program according to charts and files
Name | Role | Position | Contact Information
Feras | programmer | Manager | AD0039@iu.edu.jo
Abdulrahman | Project Interior design | designer | AD0068@iu.edu.jo
Mohammed | Project interface design | designer | AD0098@iu.edu.jo
Mohammed Adel | Problem analysis | analyst | AD0485@iu.edu.jo
Ibrahem | solving problems | analyst | AD0484@iu.edu.jo
Osaid | Project Interior design | designer | AD0953@iu.edu.jo

## Slide 10: Activity Lists
the activity name | activity identifier or number | brief description of the activity
Interface Design | 1 | The interface will be created for the project
Code | 2 | The code will start writing as required
Interior Design | 3 | The project's internal system will be designed and include all information within the project
Defining the problem | 4 | Research if there are problems in the code or design
Solve the problem | 5 | Solving existing problems (if any)

## Slide 11: GantT Chart for Project
Chart: Gantt Chart
| Interface Design | Code | Interior Design | Defining The Problem | Solve The Problem
Column2 | 44875 | 44890 | 44905 | 44920 | 44936
Column3 | 15 | 15 | 15 | 21 | 10